Strategic Plan Work Plans

# Strategic Commitment:  Polk County Academy

Goal:  The Polk County Academy will provide distinct and continuous Positive Behavior Support trainings to members of the Network and other providers in the State of Iowa.

| Objective #1: The Polk County Academy will offer quarterly training to members of the Network and providers in the State of Iowa. This training will be designed with recommendations from the network and Leadership and will align with the current strategic plan. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Attain recommendations from leadership Completed at the May monthly meeting/ Quarterly | Bill | 4-1 Quarterly | 5-1 Quarterly | 5-1-08 Quarterly |
| Set dates and months to offer training Will attempt to schedule the 2nd or 3rd week of the last month of each quarter. (September, December, March, June 08’, September 09) | Michelle | 4-1 | 5-1 | 5-1-08 |
| Set a training schedule December 11th & 12th, and March with Dr. Pomerantz. June 24th/25th- Maria V and Geery Howe. | Bill | 4-1 | 6-1 | 9-22-08 |
| Review evaluations and recommendations Ongoing, reviewed last training. | Jeff | 4-1 | 6-1 | 8-08-08 12-22-08 |
| Recruit for training Q1 to Q2 | Jan | 5-1 | Done | 9-22-08 |
| Recruit for training Q3 to Q4 | Michelle | 10-1 | 12-1 | 11-20-08 |
| Ongoing evaluation | Jeff | 8-1 | Ongoing |  |

| Objective #2: The Polk County Academy will develop a course for PBS 101. This will include the introduction to philosophy, self reflection and strategies for intervention. It will also include further instruction on ABC’s, Proactive vs. Reactive Reponses, Universal Enhance ments, Environmental Influences, and Data Assessment. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Research developed training for PBS 101. Committee reviewed 10 possible curriculums. | Jeff & Michelle | 7-08 | 9-08 | 8-08 |
| Research curriculum development from ISU We did not choose to go this route. | Jeff & Michelle | 7-08 | 9-08 | 8-08 |
| Make recommendation to Leadership | Bill | 8-08 | 10-08 | 10-08 |
| Time to purchase or develop | Academy team | 10-08 | 1-09 | 11-25-08 |
| Academy becomes familiar curriculum and designs roll out | Jan | 1-09 | 3-09 |  |
| Academy completes trial training | Dave | 12-17-08 | 12-17-08 | 12-17-08 |
| Advertise | PTNL | 4-09 | 6-09 |  |
| Train the Trainers | PTNL | 4-09 | 6-09 |  |
| PBS 101 goes live | Academy | 7-09 | 9-09 |  |

| Objective #3: The Polk County Academy will develop a course for PBS 201. This will include courses on leading change, Policy Design & Implementation, Data Assessment cont., and team building. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Research developed training for PBS 201. We have not started yet. Leadership attending Gerry Howe will Develop | Dave | 3-09 | 9-09 |  |
| Research curriculum . Leadership attending Gerry Howe will Develop | Dave | 3-09 | 9-09 |  |
| Make recommendation to Leadership | Dave | 9-08 | 10-09 |  |
| Time to develop | Dave | 10-09 | 1-10 |  |
| Academy becomes familiar with developed curriculum and designs roll out | Jan | 1-10 | 3-10 |  |
| Advertise | PTNL | 4-10 | 6-10 |  |
| Train the Trainers | PTNL | 4-10 | 6-10 |  |
| PBS 201 goes live | Academy | 7-10 | 9-10 |  |

| Objective #4: The Polk County Academy will offer Quarterly educational emails that offer links to resources and articles to further provide additional educational opportunities. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Website research- Quarterly see below | PTNL | 7-08 | 9-08 | 9-08 |
| Take recommendations- Quarterly see below | PTNL | 7-08 | 9-08 | 9-08 |
| Ongoing Process |  |  |  |  |
| Take recommendations |  |  |  |  |
| Research relevant topics and ideas |  |  |  |  |
| Academy committee approves |  |  |  |  |
| Send out email by end of each Quarter Sent in September and December 08, due March, June, September, December 09’ | Rotates quarterly | 7-08 9-08 12-08 3-09 6-09 9-09 12-09 | 9-08 12-08 | 9-08 12-08 |