Strategic Plan Work Plans

7/1/10-6/30/12

# Strategic Commitment:  Polk County Operations

Goal #1:  Provide support to teams and coaches

| Objective #1: Develop and evaluate orientation and re-orientation strategies. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Route a rough draft of the on-boarding manual to Operations Committee | Val | 6/15/10 | 7/15/10 |  |
| Revisions to manual completed | Committee | 7/15/10 | 8/1/10 |  |
| Manual to EXEC committee for review and feedback | Val | 8/1/10 | 8/15/10 |  |
| Revisions to manual completed | Committee | 8/15/10 | 9/1/10 |  |
| Manual to Board for review and approval | Val | 9/1/10 | 9/10/10 |  |
| Develop a timeline for implementation of mentoring program | TBD | 8/1/10 | 8/15/10 |  |
| EXEC committee review and approve plan | TBD | 10/10 | 10/10 |  |
| Board approval final recommendations | TBD | 11/10 | 11/10 |  |
| Implementation | TBD | 9/10/10 | 11/1/10 |  |

| Objective #2: Assess use of Fidelity Tool |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Determine partnering agency assignments | Robin | 6/10 | 6/10 |  |
| Send notice to agencies | Robin | 6/10 | 9/10 |  |
| Review results in Board meeting | All | 11/10 | 11/10 |  |
| Review of fidelity tool and guidelines | All | 2/12 | 4/12 |  |
| Development of annual schedule of review | Robin | 5/12 | 5/12 |  |

| Objective #3: Identify the purpose of the network as a training consortium or learning community and develop strategies that support the development of purpose. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Discuss at Committee | LU/Sara | 6/11 | 6/11 |  |
| Review at Board meeting and identify purpose | LU/Sara | 7/11 | 7/11 |  |
| Develop strategies | ALL | 8/11 | 8/11 |  |
| EXEC committee review and discuss | ALL | 1/12 | 1/12 |  |
| CEO input | Board | 1/12 | 1/12 |  |

Goal #2:  Enhance Network Accountability.

| Objective #1: Develop return on investment measures |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Discussion of measures at committee | TBD | 2/12 | 2/12 |  |
| Develop initial measures | TBD | 3/12 | 4/12 |  |
| Executive Committee review and discuss | TBD | 5/12 | 5/12 |  |
| Revisions and changes as needed | TBD | 6/12 | 6/12 |  |
| Board review for feedback | TBD | 7/12 | 7/12 |  |
| CEO input | TBD | 7/12 | 7/12 |  |

| Objective #2: Enhance reporting and utilization of PBS outcomes. |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| Review quarterly outcomes at Operation Committee | Dave | Oct Jan Apr Jul | On-going |  |
| Summary of outcomes at Board meeting | Dave | Nov Feb May Aug |  |  |
| Agency notification of missing quarterly data with plan of correction | Committee Chair | Oct, Jan, Apr, Jul | On-going |  |
| Development of specific work plan related to review and utilization of outcomes | Committee | 7/10 | 9/10 |  |

Goal #3:  To create Network Operations, Policy & Procedures

| Objective #1: Develop a tiered payment structure |
| --- |
| Task | Lead Person | Start Date | Target Completion Date | Actual Completion Date |
| EXEC committee discussion and recommendations | LU | 3/12 | 3/12 |  |
| Develop policy | April | 4/12 | 4/12 |  |
| EXEC committee review | All | 5/12 | 5/12 |  |
| Board approval | All | 6/12 | 6/12 |  |
| Implementation of payment structure | David | 6/12 | 6/12 |  |

# Strategic Commitment:  Polk County Operations

Pinnacle Issue:  The Polk County PBS Network is expanding.  Current practices do not provide opportunities to support new and existing teams.

Goal #1:  Provide support to teams and coaches

| Objective #: | Objective Description (General): | Priority: |
| --- | --- | --- |
| 1 | Develop and evaluate orientation and re-orientation strategies | 1 |
| 2 | Assess use of Fidelity Tool | 1 |
| 3 | Develop mentoring program | 3 |
| 4 | Identify the purpose of the network as a training consortium or learning community and develop strategies that support the development of purpose | 2 |

Goal #2: Enhance Network Accountability

| Objective #: | Objective Description (General): | Priority: |
| --- | --- | --- |
| 1 | Develop return on investment measures | 2 |
| 2 | Enhance reporting and utilization of PBS outcomes | 1 |

Goal #3: To create Network Operations, Policy and Procedures

| Objective #: | Objective Description (General): | Priority: |
| --- | --- | --- |
| 1 | Develop a tiered payment structure | 3 |